## Foglio1
|  | ATR |  | InfoIGEA |  | Team DEV |  |  | Team DATA |  | Team IT
ID | Activity | Team IT | Management | Project Manager | Management | Senior | Front-End | Back-End | Senior | Junior | Senior | Junior
1 | Vehicle maintenance management system
1.1 | System Implementation
1.1.1 | System design |  | I | R | I | R, A | I | C | C | I | C | I
1.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
1.1.3 | System Build |  |  | R |  | A |  | C
1.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
1.2 | Data Merging
1.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
1.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
1.2.3 | Development | C |  | R | I |  |  |  | A | A
1.3 | System Installation
1.3.1 | Hw configuration | C | C | R | [6 empty] | R, A | A
1.3.2 | Sw configuration | C | I | R |  | C |  |  |  |  | R, A | A
1.3.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
2 | Vehicle tracking system
2.1 | System Implementation
2.1.1 | System design |  | I | R | I | R, A | I | C | C | I | C | I
2.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
2.1.3 | System Build |  |  | R |  | A |  | C
2.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
2.2 | System Installation
2.2.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
2.2.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
2.2.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
3 | Workshop Management
3.1 | System Implementation
3.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
3.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
3.1.3 | System Build |  |  | R |  | A |  | C
3.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
3.2 | Data Merging
3.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
3.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
3.2.3 | Development | C |  | R | I |  |  |  | A | A
3.3 | System Installation
3.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
3.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
3.3.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
4 | Workshop frontend and API getaway System
4.1 | API Getaway Implementation
4.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
4.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
4.1.3 | System Build |  |  | R |  | A |  | C
4.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
4.2 | FrontEnd Implementation
4.2.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
4.2.2 | System Development |  |  | R |  | A | I | A | I |  | I
4.2.3 | System Build |  |  | R |  | A |  | C
4.2.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
4.3 | System Installation
4.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
4.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
5 | Tickets and subscription management system
5.1 | System Implementation
5.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
5.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
5.1.3 | System Build |  |  | R |  | A |  | C
5.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
5.2 | Data Merging of existing Tickets System
5.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
5.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
5.2.3 | Development | C |  | R | I |  |  |  | A | A
5.3 | Data merging of existing subscription System
5.3.1 | Analysis | C | I | R | I | I |  |  | R, A | C
5.3.2 | Design | C | I | R | I | C |  |  | R, A | A | C
5.3.3 | Development | C |  | R | I |  |  |  | A | A
5.4 | System Installation
5.4.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
5.4.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
5.4.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
6 | Customer Management System
6.1 | System Implementation
6.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
6.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
6.1.3 | System Build |  |  | R |  | A |  | C
6.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
6.2 | Data Merging
6.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
6.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
6.2.3 | Development | C |  | R | I |  |  |  | A | A
6.3 | System Installation
6.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
6.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
6.3.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
7 | Customers Frontend and PI Getaway system
7.1 | API Getaway implementation
7.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
7.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
7.1.3 | System Build |  |  | R |  | A |  | C
7.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
7.2 | Frontend implementation
7.2.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
7.2.2 | System Development |  |  | R |  | A | I | A | I |  | I
7.2.3 | System Build |  |  | R |  | A |  | C
7.2.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
7.3 | System Installation
7.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
7.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
8 | Employees Management System
8.1 | System Implementation
8.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
8.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
8.1.3 | System Build |  |  | R |  | A |  | C
8.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
8.2 | Data Merging
8.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
8.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
8.2.3 | Development | C |  | R | I |  |  |  | A | A
8.3 | System Installation
8.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
8.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
8.3.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
9 | Controllers Management System
9.1 | System Implementation
9.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
9.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
9.1.3 | System Build |  |  | R |  | A |  | C
9.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
9.2 | Data merging
9.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
9.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
9.2.3 | Development | C |  | R | I |  |  |  | A | A
9.3 | System Installation
9.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
9.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
9.3.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
10 | Drivers Management System
10.1 | System Implementation
10.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
10.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
10.1.3 | System Build |  |  | R |  | A |  | C
10.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
10.2 | Data Merging
10.2.1 | Analysis | C | I | R | I | I |  |  | R, A | C
10.2.2 | Design | C | I | R | I | C |  |  | R, A | A | C
10.2.3 | Development | C |  | R | I |  |  |  | A | A
10.3 | System Installation
10.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
10.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A
10.3.3 | Data Merging Configuration | C | I | R |  |  |  |  | C |  | R, A | A
11 | Employees Frontend and API Getaway System
11.1 | API Getaway Implementation
11.1.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
11.1.2 | System Development |  |  | R |  | A | I | A | I |  | I
11.1.3 | System Build |  |  | R |  | A |  | C
11.1.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
11.2 | Frontend Implementation
11.2.1 | System Design |  | I | R | I | R, A | I | C | C | I | C | I
11.2.2 | System Development |  |  | R |  | A | I | A | I |  | I
11.2.3 | System Build |  |  | R |  | A |  | C
11.2.4 | System Test |  |  | R | I | R, A |  | A |  |  | C
11.3 | System Installation
10.3.1 | HW Configuration | C | C | R | [6 empty] | R, A | A
10.3.2 | SW Configuration | C | I | R |  | C |  |  |  |  | R, A | A