## Riassunto
|  | Team Cost | Travel Cost | Software cost
Estimated Cost | 1149040 | 401240 | 107080 | 640720
Actual Cost | 1172340 | 410880 | 107300 | 654160 |  |  | Monney | Percentual
Difference | 23300 | 9640 | 220 | 13440 |  | First Milestone | 600000 | 30%
Fixed addition | 50000 |  |  |  |  | Second Milestone | 700000 | 35%
Tender Documentation | 2000000 |  |  |  |  | Third milestone | 700000 | 35%
Total Earned | 827660
| Cost |  | Effort
| Estimated | Actual | Estimated | Actual
Phase 1 | 46840 | 46840 | 248 | 248
Phase 2 | 73540 | 73540 | 472 | 472
Phase 3 | 69610 | 69610 | 488 | 488
Phase 4 | 143070 | 143070 | 960 | 960
Phase 5 | 78010 | 78010 | 528 | 528
Phase 6 | 96680 | 96680 | 720 | 720 | Milestone 1 | 507750
Phase 7 | 120300 | 130150 | 720 | 856
Phase 8 | 104710 | 104710 | 752 | 752
Phase 9 | 104710 | 104710 | 752 | 752
Phase 10 | 103870 | 103870 | 752 | 752 | Milestone 2 | 433590
Phase 11 | 136870 | 136870 | 944 | 944
Phase 12 | 23610 | 37060 | 256 | 376
Phase 13 | 23610 | 23610 | 256 | 256
Phase 14 | 23610 | 23610 | 256 | 256 | Milestone 3 | 207700
| 1149040 | 1172340 | 8104 | 8360
| CV | 2.028% | SV | 3.159%
| Team Cost |  |  |  | Travel cost |  |  |  | Software Cost
| Project Manager - Team Cost | DEV Team - Team Cost | DATA Team - Team Cost | IT Team - Team cost | Project Manager -Travel Cost | DEV Team - Travel Cost | DATA Team - Travel Cost | IT Team - Travel Cost | Project Manager - Software Cost | DEV Team - Software Cost | DATA Team - Software Cost | IT Team - Software Cost
Phase 1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0
Phase 2 | 1200 | 12960 | 9920 | 0 | 920 | 0 | 4780 | 0 | 0 | 32400 | 11360 | 0
Phase 3 | 1200 | 12960 | 0 | 11160 | 920 | 0 | 0 | 5210 | 0 | 32400 | 0 | 5760
Phase 4 | 1600 | 22520 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 69600 | 11360 | 5760
Phase 5 | 1200 | 15360 | 0 | 11160 | 920 | 0 | 0 | 5210 | 0 | 38400 | 0 | 5760
Phase 6 | 1600 | 15360 | 9920 | 9840 | 1160 | 0 | 4780 | 4260 | 0 | 38400 | 11360 | 0
Phase 7 | 1600 | 22520 | 9920 | 6240 | 1160 | 0 | 4780 | 2970 | 0 | 69600 | 11360 | 0
Phase 8 | 1600 | 15360 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 5760
Phase 9 | 1600 | 15360 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 5760
Phase 10 | 1200 | 15360 | 9920 | 11160 | 720 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 5760
Phase 11 | 1600 | 22520 | 9920 | 11160 | 720 | 0 | 4780 | 5210 | 0 | 69600 | 11360 | 0
Phase 12 | 1000 | 2800 | 0 | 11160 | 800 | 0 | 0 | 2100 | 0 | 13440 | 0 | 5760
Phase 13 | 800 | 0 | 0 | 11160 | 680 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
Phase 14 | 800 | 0 | 0 | 11160 | 680 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
| Team Cost |  |  |  | Travel cost |  |  |  | Software Cost
| Project Manager | DEV Team | DATA Team | IT Team | Project Manager | DEV Team | DATA Team | IT Team | Project Manager | DEV Team | DATA Team | IT Team
Phase 1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0
Phase 2 | 1200 | 12960 | 9920 | 0 | 920 | 0 | 4780 | 0 | 0 | 32400 | 11360 | 0
Phase 3 | 1200 | 12960 | 0 | 11160 | 920 | 0 | 0 | 5210 | 0 | 32400 | 0 | 5760
Phase 4 | 1600 | 22520 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 69600 | 11360 | 5760
Phase 5 | 1200 | 15360 | 0 | 11160 | 920 | 0 | 0 | 5210 | 0 | 38400 | 0 | 5760
Phase 6 | 1600 | 15360 | 9920 | 9840 | 1160 | 0 | 4780 | 4260 | 0 | 38400 | 11360 | 0
Phase 7 | 1600 | 22520 | 9920 | 6240 | 1160 | 0 | 4780 | 2970 | 0 | 69600 | 11360 | 0
Phase 8 | 1600 | 15360 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 5760
Phase 9 | 1600 | 15360 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 5760
Phase 10 | 1200 | 15360 | 9920 | 11160 | 720 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 5760
Phase 11 | 1600 | 22520 | 9920 | 11160 | 720 | 0 | 4780 | 5210 | 0 | 69600 | 11360 | 0
Phase 12 | 1000 | 2800 | 0 | 11160 | 800 | 0 | 0 | 2100 | 0 | 13440 | 0 | 5760
Phase 13 | 800 | 0 | 0 | 11160 | 680 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
Phase 14 | 800 | 0 | 0 | 11160 | 680 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
| 17800 | 186040 | 79360 | 127680 | 12840 | 0 | 38240 | 56220 | 0 | 511440 | 90880 | 51840
| Cost |  |  | Effort |  |  | Cost |  |  | Effort
Activity ID | Estimated | Actual | When the PM Travels | Estimated | Actual |  | Estimated | Actual |  | Estimated | Actual | Milestone | Estimated | Actual
1.1 | 46840 | 46840 | PHASE 1 | 248 | 248 | 1 | 96310 | 96310 |  | 712 | 712 | 1 | 2616 | 2752
1.2 | 26700 | 26700 |  | 224 | 224 | 2 | 69610 | 69610 |  | 488 | 488 | 2 | 2464 | 2464
1.3 | 22770 | 22770 |  | 240 | 240 | 3 | 96310 | 96310 |  | 712 | 712 | 3 | 3040 | 3160
2.1 | 46840 | 46840 | PHASE 2 | 248 | 248 | 4 | 108340 | 118190 |  | 704 | 840
2.2 | 22770 | 22770 |  | 240 | 240 | 5 | 139810 | 139810 |  | 1016 | 1016
3.1 | 46840 | 46840 | PHASE 3 | 248 | 248 | 6 | 96310 | 96310 |  | 712 | 712
3.2 | 26700 | 26700 |  | 224 | 224 | 7 | 116370 | 116370 |  | 736 | 736
3.3 | 22770 | 22770 |  | 240 | 240 | 8 | 98950 | 98950 |  | 752 | 752
4.1 | 49880 | 49880 | PHASE 4 | 256 | 256 | 9 | 113110 | 107900 |  | 792 | 792
4.2 | 43720 | 43720 |  | 240 | 240 | 10 | 97150 | 97150 |  | 728 | 728
4.3 | 14740 | 24590 |  | 208 | 344 | 11 | 118050 | 140070 |  | 768 | 888
5.1 | 55240 | 55240 | PHASE 5 | 288 | 288
5.2 | 35100 | 35100 |  | 264 | 264
5.3 | 26700 | 26700 |  | 224 | 224
5.4 | 22770 | 22770 |  | 240 | 240
6.1 | 46840 | 46840 | PHASE 6 | 248 | 248
6.2 | 26700 | 26700 |  | 224 | 224
6.3 | 22770 | 22770 |  | 240 | 240
7.1 | 49880 | 49880 | PHASE 7 | 256 | 256
7.2 | 43720 | 43720 |  | 240 | 240
7.3 | 22770 | 22770 |  | 240 | 240
8.1 | 55240 | 55240 | PHASE 8 | 288 | 288
8.2 | 26700 | 26700 |  | 224 | 224
8.3 | 17010 | 17010 |  | 240 | 240
9.1 | 55240 | 55240 | PHASE 9 | 288 | 288
9.2 | 35100 | 35100 |  | 264 | 264
9.3 | 22770 | 17560 |  | 240 | 240
10.1 | 46840 | 46840 | PHASE 10 | 248 | 248
10.2 | 26700 | 26700 |  | 224 | 224
10.3 | 23610 | 23610 | PHASE 13 | 256 | 256
11.1 | 49880 | 49880 | PHASE 11 | 256 | 256
11.2 | 44560 | 66580 | PHASE 12 | 256 | 376
11.3 | 23610 | 23610 | PHASE 14 | 256 | 256
| 1150320 | 1176980
| Estimated | Actual | % Cost | Estimated | Actual | % Time | (Est-Act)/Act
Milestone 1 | 370570 | 380420 | 32.32% | 2616 | 2752 | 32.86% | 4.942%
Milestone 2 | 352490 | 352490 | 29.95% | 2464 | 2464 | 29.42% | 0%
Milestone 3 | 427260 | 444070 | 37.73% | 3040 | 3160 | 37.73% | 3.797%
|  |  |  | 8120 | 8376 |  | 3.056%
| Team Cost |  |  |  | Travel cost |  |  |  | Software Cost
Activity ID | Project Manager -Team Cost | DEV Team -Team Cost | DATA Team -Team Cost | IT Team - Team Cost | Project Manager - Travel Cost | DEV Team - Travel Cost | DATA Team - Travel Cost | IT Team - Travel Cost | Project Manager - Software Cost | DEV Team - Software Cost | DATA Team - Software Cost | IT Team - Software Cost | When the PM Travels
1.1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0 | PHASE 1
1.2 | 400 | 0 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 0 | 11360 | 0
1.3 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
2.1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0 | PHASE 2
2.2 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
3.1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0 | PHASE 3
3.2 | 400 | 0 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 0 | 11360 | 0
3.3 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
4.1 | 600 | 13920 | 0 | 0 | 560 | 0 | 0 | 0 | 0 | 34800 | 0 | 0 | PHASE 4
4.2 | 200 | 8600 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 34800 | 0 | 0
4.3 | 800 | 0 | 0 | 16080 | 480 | 0 | 0 | 7230 | 0 | 0 | 0 | 0
5.1 | 800 | 15360 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 38400 | 0 | 0 | PHASE 5
5.2 | 400 | 2400 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 6000 | 11360 | 0
5.3 | 400 | 0 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 0 | 11360 | 0
5.4 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
6.1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0 | PHASE 6
6.2 | 400 | 0 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 0 | 11360 | 0
6.3 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
7.1 | 600 | 13920 | 0 | 0 | 560 | 0 | 0 | 0 | 0 | 34800 | 0 | 0 | PHASE 7
7.2 | 200 | 8600 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 34800 | 0 | 0
7.3 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760
8.1 | 800 | 15360 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 38400 | 0 | 0 | PHASE 8
8.2 | 400 | 0 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 0 | 11360 | 0
8.3 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 5210 | 0 | 0 | 0 | 0
9.1 | 800 | 15360 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 38400 | 0 | 0 | PHASE 9
9.2 | 400 | 2400 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 6000 | 11360 | 0
9.3 | 400 | 0 | 0 | 11160 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 5760
10.1 | 800 | 12960 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 32400 | 0 | 0 | PHASE 10
10.2 | 400 | 0 | 9920 | 0 | 240 | 0 | 4780 | 0 | 0 | 0 | 11360 | 0
10.3 | 800 | 0 | 0 | 11160 | 680 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760 | PHASE 13
11.1 | 600 | 13920 | 0 | 0 | 560 | 0 | 0 | 0 | 0 | 34800 | 0 | 0 | PHASE 11
11.2 | 800 | 11400 | 0 | 0 | 680 | 0 | 0 | 2100 | 0 | 51600 | 0 | 0 | PHASE 12
11.3 | 800 | 0 | 0 | 11160 | 680 | 0 | 0 | 5210 | 0 | 0 | 0 | 5760 | PHASE 14
| Team Cost |  |  |  | Travel cost |  |  |  | Software Cost
Activity ID | Project Manager -Team Cost | DEV Team -Team Cost | DATA Team -Team Cost | IT Team - Team Cost | Project Manager - Travel Cost | DEV Team - Travel Cost | DATA Team - Travel Cost | IT Team - Travel Cost | Project Manager - Software Cost | DEV Team - Software Cost | DATA Team - Software Cost | IT Team - Software Cost
1 | 1600 | 12960 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 32400 | 11360 | 5760
2 | 1200 | 12960 | 0 | 11160 | 920 | 0 | 0 | 5210 | 0 | 32400 | 0 | 5760
3 | 1600 | 12960 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 32400 | 11360 | 5760
4 | 1600 | 22520 | 0 | 16080 | 1160 | 0 | 0 | 7230 | 0 | 69600 | 0 | 0
5 | 2000 | 17760 | 19840 | 11160 | 1400 | 0 | 9560 | 5210 | 0 | 44400 | 22720 | 5760
6 | 1600 | 12960 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 32400 | 11360 | 5760
7 | 1200 | 22520 | 0 | 11160 | 920 | 0 | 0 | 5210 | 0 | 69600 | 0 | 5760
8 | 1600 | 15360 | 9920 | 11160 | 1160 | 0 | 4780 | 5210 | 0 | 38400 | 11360 | 0
9 | 1600 | 17760 | 9920 | 11160 | 1160 | 0 | 4780 | 0 | 0 | 44400 | 11360 | 5760
10 | 2000 | 12960 | 9920 | 11160 | 1600 | 0 | 4780 | 5210 | 0 | 32400 | 11360 | 5760
11 | 2200 | 25320 | 0 | 11160 | 1920 | 0 | 0 | 7310 | 0 | 86400 | 0 | 5760

## RiferimentiCosti
Team Cost | [8 empty] | Travel costs | [5 empty] | Software costs
| DEV Team |  |  | DATA team |  | IT team |  |  |  | DATA Team |  | IT Team |  |  | DEV Team |  | DATA team |  | IT team
Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Total cost Team | Project Manager | Senior | Junior | Senior | Junior | Total Budget travel | Development Software | Cloud Services | Software Data | Cloud Servicies | Cloud Servicies | Total cost Team
25 | 60 | 60 | 25 | 57.5 | 42.5 | 60 | 45 |  | 120 | 150 | 140 | 150 | 140 |  | 30 | 120 | 20 | 50 | 80
per ora | per ora | per ora | per ora | per ora | per ora | per ora | per ora |  | per gg (/8 h) | per gg (/8h) | per gg (/8h) | per gg (/8h) | per gg (/8h) |  | per gg (/8h) | per gg (/8h) | per gg (/8h) | per gg (/8h) | per gg (/8h)
[9 empty] | 200 | 150 | 150 | 200 | 200
[9 empty] | per sprint | per week | per week | per week | per week

## Cost
| Team Cost | [8 empty] | Travel costs | [5 empty] | Software costs
|  | DEV Team |  |  | DATA team |  | IT team |  |  |  | DATA Team |  | IT Team |  |  | DEV Team |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Total cost Team | Project Manager | Senior | Junior | Senior | Junior | Total Budget travel | Development Software | Cloud Services | Software Data | Cloud Servicies | Cloud Servicies | Total cost Team | Total cost
PHASE 1 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | [5 empty] | 0 | 840
1.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
1.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
1.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
1.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
1.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
Total | 800 | 4320 | 8640 | 0 | 0 | 0 | 0 | 0 | 13760 | 680 | 0 | 0 | 0 | 0 | 680 | 6480 | 25920 | 0 | 0 | 0 | 32400 | 46840
PHASE 2 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
2.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
2.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
2.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
2.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
2.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
1.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
1.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
1.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
1.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
Total | 1200 | 4320 | 8640 | 0 | 4140 | 5780 | 0 | 0 | 24080 | 920 | 1800 | 2980 | 0 | 0 | 5700 | 6480 | 25920 | 4160 | 7200 | 0 | 43760 | 73540
PHASE 3 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
3.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
3.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
3.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
3.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
3.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
1.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1200 | 4320 | 8640 | 0 | 0 | 0 | 4320 | 6840 | 25320 | 920 | 0 | 0 | 1950 | 3260 | 6130 | 6480 | 25920 | 0 | 0 | 5760 | 38160 | 69610 | 0
PHASE 4 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
4.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
4.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
4.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
4.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
4.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 10080
4.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
4.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8120
4.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 19880
4.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6160
4.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9240
3.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
3.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
3.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
3.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
2.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1600 | 9600 | 9120 | 3800 | 4140 | 5780 | 4320 | 6840 | 45200 | 1160 | 1800 | 2980 | 1950 | 3260 | 11150 | 13920 | 55680 | 4160 | 7200 | 5760 | 86720 | 143070 | 0
PHASE 5 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
5.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
5.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
5.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
5.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
5.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
3.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1200 | 6240 | 9120 | 0 | 0 | 0 | 4320 | 6840 | 27720 | 920 | 0 | 0 | 1950 | 3260 | 6130 | 7680 | 30720 | 0 | 0 | 5760 | 44160 | 78010 | 0
PHASE 6 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
6.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
6.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
6.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
6.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
5.2 | 400 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2800 | 240 | 0 | 0 | 0 | 0 | 240 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 9040
5.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
4.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2520 | 4920 | 0 | 0 | 0 | 950 | 1180 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2520 | 4920 | 0 | 0 | 0 | 950 | 1180 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
Total | 1600 | 6240 | 9120 | 0 | 4140 | 5780 | 4800 | 5040 | 36720 | 1160 | 1800 | 2980 | 1900 | 2360 | 10200 | 7680 | 30720 | 4160 | 7200 | 0 | 49760 | 96680 | 0
PHASE 7 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
7.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
7.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
7.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
7.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
7.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 10080
7.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
7.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8120
7.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 19880
7.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6160
7.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9240
5.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
5.3.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.3.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.3.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
Total | 1200 | 9600 | 9120 | 3800 | 4140 | 5780 | 0 | 0 | 33640 | 920 | 1800 | 2980 | 0 | 0 | 5700 | 13920 | 55680 | 4160 | 7200 | 0 | 80960 | 120300 | 0
PHASE 8 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
8.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
8.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
8.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
8.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
8.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
6.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
6.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
6.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
6.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
5.4 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1600 | 6240 | 9120 | 0 | 4140 | 5780 | 4320 | 6840 | 38040 | 1160 | 1800 | 2980 | 1950 | 3260 | 11150 | 7680 | 30720 | 4160 | 7200 | 5760 | 55520 | 104710 | 0
PHASE 9 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
9.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
9.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
9.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
9.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
9.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
8.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
8.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
8.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
8.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
6.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1600 | 6240 | 9120 | 0 | 4140 | 5780 | 4320 | 6840 | 38040 | 1160 | 1800 | 2980 | 1950 | 3260 | 11150 | 7680 | 30720 | 4160 | 7200 | 5760 | 55520 | 104710 | 0
PHASE 10 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
10.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
10.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
10.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
10.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
9.2 | 400 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2800 | 240 | 0 | 0 | 0 | 0 | 240 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 9040
9.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
9.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
9.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
7.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1200 | 6240 | 9120 | 0 | 4140 | 5780 | 4320 | 6840 | 37640 | 720 | 1800 | 2980 | 1950 | 3260 | 10710 | 7680 | 30720 | 4160 | 7200 | 5760 | 55520 | 103870 | -840
PHASE 11 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
11.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
11.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
11.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
11.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
11.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 10080
11.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
11.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8120
11.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 19880
11.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6160
11.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9240
10.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
10.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
10.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
10.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
8.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
8.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
8.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
8.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
Total | 1600 | 9600 | 9120 | 3800 | 4140 | 5780 | 4320 | 6840 | 45200 | 720 | 1800 | 2980 | 1950 | 3260 | 10710 | 13920 | 55680 | 4160 | 7200 | 0 | 80960 | 136870
PHASE 12 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
9.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
9.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 800 | 0 | 0 | 0 | 0 | 0 | 4320 | 6840 | 11960 | 680 | 0 | 0 | 1950 | 3260 | 5890 | 0 | 0 | 0 | 0 | 5760 | 5760 | 23610
PHASE 13 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
10.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
10.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
10.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
10.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 800 | 0 | 0 | 0 | 0 | 0 | 4320 | 6840 | 11960 | 680 | 0 | 0 | 1950 | 3260 | 5890 | 0 | 0 | 0 | 0 | 5760 | 5760 | 23610
PHASE 14 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
11.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
11.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
11.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
11.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 800 | 0 | 0 | 0 | 0 | 0 | 4320 | 6840 | 11960 | 680 | 0 | 0 | 1950 | 3260 | 5890 | 0 | 0 | 0 | 0 | 5760 | 5760 | 23610
TOTAL | 17200 | 72960 | 98880 | 11400 | 33120 | 46240 | 48000 | 73440 | 401240 | 12480 | 14400 | 23840 | 21400 | 34960 | 107080 | 99600 | 398400 | 33280 | 57600 | 51840 | 640720 | 1149040
[21 empty] | 640720 | 640720

## Effort
|  | DEV Team |  |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Effort
PHASE 1 | 16 | [7 empty] | 16
1.1 | 16 | [5 empty] | 0 | 0 | 16
1.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
1.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
1.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
1.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
Total | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 248
PHASE 2 | 16 | [7 empty] | 16
2.1 | 16 | [7 empty] | 16
2.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 16 | [7 empty] | 16
1.2.1 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 16 | [7 empty] | 16
3.1 | 16 | [7 empty] | 16
3.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 16 | [7 empty] | 16
1.3.1 |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 16 | [7 empty] | 16
4.1 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 |  | 32 | 8 | [5 empty] | 40
4.1.2 |  | 8 | 104 | [5 empty] | 112
4.1.3 |  | 16 | 16 | [5 empty] | 32
4.1.4 |  | 24 | 24 | [5 empty] | 48
4.2 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 |  |  |  |  | 24 | 8 |  |  | 32
3.2.2 |  |  |  |  | 24 | 8 |  |  | 32
3.2.3 |  |  |  |  | 24 | 120 |  |  | 144
2.2 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | [6 empty] | 24 | 56 | 80
2.2.2 | [6 empty] | 24 | 48 | 72
2.2.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 40 | 56 | 96
4.3.2 | [6 empty] | 40 | 56 | 96
Total | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
Milesone 1
PHASE 7 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144
Total | 48 | 160 | 152 | 152 | 72 | 136 | 0 | 0 | 720
PHASE 8 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 24 | 8 |  |  | 32
8.2.2 |  |  |  |  | 24 | 8 |  |  | 32
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 10 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40
9.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
Milestone 2
PHASE 11 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8
11.2.1 |  | 32 |  | 8 |  |  |  |  | 40
11.2.2 |  | 8 |  | 104 |  |  |  |  | 112
11.2.3 |  | 16 |  | 16 |  |  |  |  | 32
11.2.4 |  | 24 |  | 24 |  |  |  |  | 48
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 944
PHASE 12 | 16 | [7 empty] | 16
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 13 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
Total (hours) | 672 | 1216 | 1648 | 456 | 576 | 1088 | 800 | 1632 | 8088
Total (days) | 84 | 152 | 206 | 57 | 72 | 136 | 100 | 204 | 1011

## Effort effettivo
|  | DEV Team |  |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Effort
PHASE 1 | 16 | [7 empty] | 16
1.1 | 16 | [5 empty] | 0 | 0 | 16
1.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
1.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
1.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
1.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
Total | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 248
PHASE 2 | 16 | [7 empty] | 16
2.1 | 16 | [7 empty] | 16
2.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 16 | [7 empty] | 16
1.2.1 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 16 | [7 empty] | 16
3.1 | 16 | [7 empty] | 16
3.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 16 | [7 empty] | 16
1.3.1 |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 16 | [7 empty] | 16
4.1 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 |  | 32 | 8 | [5 empty] | 40
4.1.2 |  | 8 | 104 | [5 empty] | 112
4.1.3 |  | 16 | 16 | [5 empty] | 32
4.1.4 |  | 24 | 24 | [5 empty] | 48
4.2 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 |  |  |  |  | 24 | 8 |  |  | 32
3.2.2 |  |  |  |  | 24 | 8 |  |  | 32
3.2.3 |  |  |  |  | 24 | 120 |  |  | 144
2.2 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | [6 empty] | 24 | 56 | 80
2.2.2 | [6 empty] | 24 | 48 | 72
2.2.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 80 | 112 | 192 | 56 | 112
4.3.2 | [6 empty] | 0 | 0 | 0 | 56
Total | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
PHASE 7 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 16 | 8 | 24
4.3.2 | [6 empty] | 40 | 56 | 96
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144
Total | 64 | 160 | 152 | 152 | 72 | 136 | 56 | 64 | 856
Milestone 1
PHASE 8 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 24 | 8 |  |  | 32
8.2.2 |  |  |  |  | 24 | 8 |  |  | 32
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 10 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40
9.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
Milestone 2
PHASE 11 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48 | 8 | 152
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8 | 104
11.2.1 |  | 32 |  | 40 |  |  |  |  | 72 | 16
11.2.2 |  | 8 |  | 112 |  |  |  |  | 120 | 24
11.2.3 |  | 16 |  | 0 |  |  |  |  | 16
11.2.4 |  | 24 |  | 0 |  |  |  |  | 24
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 944
PHASE 12 | 16 | [7 empty] | 16
11.2 | 8 | [7 empty] | 8
11.2.1 |  |  |  | 0 |  |  |  |  | 0
11.2.2 |  |  |  | 8 |  |  |  |  | 8
11.2.3 |  |  |  | 48 |  |  |  |  | 48
11.2.4 |  |  |  | 56 |  |  |  |  | 56
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72
Total | 40 | 0 | 0 | 112 | 0 | 0 | 72 | 152 | 376
PHASE 13 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
Milestone 3
Total (hours) | 696 | 1216 | 1648 | 568 | 576 | 1088 | 856 | 1696 | 8344
Total (days) | 87 | 152 | 206 | 71 | 72 | 136 | 107 | 212 | 1043

## Cost Effettivo
| Team Cost | [8 empty] | Travel costs | [5 empty] | Software costs
|  | DEV Team |  |  | DATA team |  | IT team |  |  |  | DATA Team |  | IT Team |  |  | DEV Team |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Total cost Team | Project Manager | Senior | Junior | Senior | Junior | Total Budget travel | Development Software | Cloud Services | Software Data | Cloud Servicies | Cloud Servicies | Total cost Team | Total cost
PHASE 1 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | [5 empty] | 0 | 840
1.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
1.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
1.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
1.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
1.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
Total | 800 | 4320 | 8640 | 0 | 0 | 0 | 0 | 0 | 13760 | 680 | 0 | 0 | 0 | 0 | 680 | 6480 | 25920 | 0 | 0 | 0 | 32400 | 46840
PHASE 2 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
2.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
2.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
2.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
2.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
2.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
1.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
1.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
1.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
1.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
Total | 1200 | 4320 | 8640 | 0 | 4140 | 5780 | 0 | 0 | 24080 | 920 | 1800 | 2980 | 0 | 0 | 5700 | 6480 | 25920 | 4160 | 7200 | 0 | 43760 | 73540
PHASE 3 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
3.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
3.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
3.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
3.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
3.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
1.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1200 | 4320 | 8640 | 0 | 0 | 0 | 4320 | 6840 | 25320 | 920 | 0 | 0 | 1950 | 3260 | 6130 | 6480 | 25920 | 0 | 0 | 5760 | 38160 | 69610
PHASE 4 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
4.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
4.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
4.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
4.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
4.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 10080
4.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
4.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8120
4.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 19880
4.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6160
4.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9240
3.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
3.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
3.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
3.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
2.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1600 | 9600 | 9120 | 3800 | 4140 | 5780 | 4320 | 6840 | 45200 | 1160 | 1800 | 2980 | 1950 | 3260 | 11150 | 13920 | 55680 | 4160 | 7200 | 5760 | 86720 | 143070
PHASE 5 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
5.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
5.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
5.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
5.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
5.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
3.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1200 | 6240 | 9120 | 0 | 0 | 0 | 4320 | 6840 | 27720 | 920 | 0 | 0 | 1950 | 3260 | 6130 | 7680 | 30720 | 0 | 0 | 5760 | 44160 | 78010
PHASE 6 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
6.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
6.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
6.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
6.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
5.2 | 400 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2800 | 240 | 0 | 0 | 0 | 0 | 240 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 9040
5.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
4.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2520 | 4920 | 0 | 0 | 0 | 950 | 1180 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2520 | 4920 | 0 | 0 | 0 | 950 | 1180 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
Total | 1600 | 6240 | 9120 | 0 | 4140 | 5780 | 4800 | 5040 | 36720 | 1160 | 1800 | 2980 | 1900 | 2360 | 10200 | 7680 | 30720 | 4160 | 7200 | 0 | 49760 | 96680
PHASE 7 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
7.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
7.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
7.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
7.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
7.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 10080
7.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
7.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8120
7.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 19880
7.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6160
7.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9240
4.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 360 | 1320 | 0 | 0 | 0 | 500 | 340 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 2160
4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2520 | 4920 | 0 | 0 | 0 | 950 | 1180 | 2130 | 0 | 0 | 0 | 0 | 0 | 0 | 7050
5.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
5.3.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.3.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
5.3.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
Total | 1600 | 9600 | 9120 | 3800 | 4140 | 5780 | 3360 | 2880 | 40280 | 1160 | 1800 | 2980 | 1450 | 1520 | 8910 | 13920 | 55680 | 4160 | 7200 | 0 | 80960 | 130150
PHASE 8 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
8.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
8.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
8.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
8.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
8.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
6.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
6.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
6.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
6.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
5.4 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1600 | 6240 | 9120 | 0 | 4140 | 5780 | 4320 | 6840 | 38040 | 1160 | 1800 | 2980 | 1950 | 3260 | 11150 | 7680 | 30720 | 4160 | 7200 | 5760 | 55520 | 104710
PHASE 9 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
9.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
9.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
9.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
9.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
9.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
8.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
8.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
8.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
8.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
6.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1600 | 6240 | 9120 | 0 | 4140 | 5780 | 4320 | 6840 | 38040 | 1160 | 1800 | 2980 | 1950 | 3260 | 11150 | 7680 | 30720 | 4160 | 7200 | 5760 | 55520 | 104710
PHASE 10 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
10.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
10.1.1 | 0 | 3360 | 480 | 0 | 0 | 0 | 0 | 0 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 7680 | 0 | 0 | 0 | 9600 | 13440
10.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
10.1.3 | 0 | 1440 | 960 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
9.2 | 400 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2800 | 240 | 0 | 0 | 0 | 0 | 240 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 9040
9.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
9.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
9.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
7.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 1200 | 6240 | 9120 | 0 | 4140 | 5780 | 4320 | 6840 | 37640 | 720 | 1800 | 2980 | 1950 | 3260 | 10710 | 7680 | 30720 | 4160 | 7200 | 5760 | 55520 | 103870
PHASE 11 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
11.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
11.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8400
11.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 23520
11.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6720
11.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 10080
11.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
11.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 4800 | 0 | 0 | 0 | 6000 | 8120
11.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 13440 | 0 | 0 | 0 | 16800 | 19880
11.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 3840 | 0 | 0 | 0 | 4800 | 6160
11.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9240
10.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
10.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
10.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 | 0 | 600 | 290 | 0 | 0 | 890 | 0 | 0 | 640 | 0 | 0 | 640 | 3250
10.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 | 0 | 600 | 2400 | 0 | 0 | 3000 | 0 | 0 | 2880 | 7200 | 0 | 10080 | 19560
8.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
8.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
8.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
8.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
Total | 1600 | 9600 | 9120 | 3800 | 4140 | 5780 | 4320 | 6840 | 45200 | 720 | 1800 | 2980 | 1950 | 3260 | 10710 | 13920 | 55680 | 4160 | 7200 | 0 | 80960 | 136870
PHASE 12 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
11.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 120 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 320
11.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.2 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 150 | 0 | 150 | 240 | 960 | 0 | 0 | 0 | 1200 | 1550
11.2.3 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 900 | 0 | 900 | 1440 | 5760 | 0 | 0 | 0 | 7200 | 9300
11.2.4 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 1050 | 0 | 1050 | 1680 | 6720 | 0 | 0 | 0 | 8400 | 10850
9.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
9.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3960
9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600
9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5760 | 5760 | 9360
Total | 1000 | 0 | 0 | 2800 | 0 | 0 | 4320 | 6840 | 14960 | 800 | 0 | 0 | 2100 | 0 | 2900 | 0 | 13440 | 0 | 0 | 5760 | 19200 | 37060
PHASE 13 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
10.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
10.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
10.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
10.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 800 | 0 | 0 | 0 | 0 | 0 | 4320 | 6840 | 11960 | 680 | 0 | 0 | 1950 | 3260 | 5890 | 0 | 0 | 0 | 0 | 5760 | 5760 | 23610
PHASE 14 | 400 | [7 empty] | 400 | 440 |  |  |  |  | 440 | 0 |  |  |  |  | 0 | 840
11.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 640
11.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | 0 | 0 | 0 | 650 | 1180 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 5790
11.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 5290
11.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | 0 | 0 | 0 | 650 | 1040 | 1690 | 0 | 0 | 0 | 0 | 5760 | 5760 | 11050
Total | 800 | 0 | 0 | 0 | 0 | 0 | 4320 | 6840 | 11960 | 680 | 0 | 0 | 1950 | 3260 | 5890 | 0 | 0 | 0 | 0 | 5760 | 5760 | 23610
TOTAL | 17800 | 72960 | 98880 | 14200 | 33120 | 46240 | 51360 | 76320 | 410880 | 12840 | 14400 | 23840 | 23000 | 33220 | 107300 | 99600 | 411840 | 33280 | 57600 | 51840 | 654160 | 1172340
[9 empty] | 410880 | [5 empty] | 107300 | [5 empty] | 654160 | 1172340

## Milestone 1 (hidden)
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Effort
PHASE 1 | 16 | [7 empty] | 16
1.1 | 16 | [5 empty] | 0 | 0 | 176
1.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0
1.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0
Total | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 192
PHASE 2 | 16 | [7 empty] | 16
2.1 | 16 | [7 empty] | 16
2.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 16 | [7 empty] | 16
1.2.1 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 16 | [7 empty] | 16
3.1 | 16 | [7 empty] | 16
3.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 16 | [7 empty] | 16
1.3.1 |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 16 | [7 empty] | 16
4.1 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 |  | 32 | 8 | [5 empty] | 40
4.1.2 |  | 8 | 104 | [5 empty] | 112
4.1.3 |  | 16 | 16 | [5 empty] | 32
4.1.4 |  | 24 | 24 | [5 empty] | 48
4.2 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 |  |  |  |  | 24 | 8 |  |  | 32
3.2.2 |  |  |  |  | 24 | 8 |  |  | 32
3.2.3 |  |  |  |  | 24 | 120 |  |  | 144
2.2 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | [6 empty] | 24 | 56 | 80
2.2.2 | [6 empty] | 24 | 48 | 72
2.2.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 40 | 56 | 96
4.3.2 | [6 empty] | 40 | 56 | 96
Total | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
PHASE 7 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144
Total | 48 | 160 | 152 | 152 | 72 | 136 | 0 | 0 | 720
PHASE 8 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 24 | 8 |  |  | 32
8.2.2 |  |  |  |  | 24 | 8 |  |  | 32
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 10 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40
9.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 11 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8
11.2.1 |  | 32 |  | 8 |  |  |  |  | 40
11.2.2 |  | 8 |  | 104 |  |  |  |  | 112
11.2.3 |  | 16 |  | 16 |  |  |  |  | 32
11.2.4 |  | 24 |  | 24
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 896
PHASE 12 | 16 | [7 empty] | 16
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 13 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
Total (hours) | 672 | 1216 | 1648 | 456 | 576 | 1088 | 800 | 1632 | 8088
Total (days) | 84 | 152 | 206 | 57 | 72 | 136 | 100 | 204 | 1011

## Milestone 2 (hidden)
|  | DEV Team |  |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Effort
PHASE 1 | 16 | [7 empty] | 16
1.1 | 16 | [5 empty] | 0 | 0 | 176
1.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0
1.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0
Total | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 192
PHASE 2 | 16 | [7 empty] | 16
2.1 | 16 | [7 empty] | 16
2.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 16 | [7 empty] | 16
1.2.1 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 16 | [7 empty] | 16
3.1 | 16 | [7 empty] | 16
3.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 16 | [7 empty] | 16
1.3.1 |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 16 | [7 empty] | 16
4.1 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 |  | 32 | 8 | [5 empty] | 40
4.1.2 |  | 8 | 104 | [5 empty] | 112
4.1.3 |  | 16 | 16 | [5 empty] | 32
4.1.4 |  | 24 | 24 | [5 empty] | 48
4.2 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 |  |  |  |  | 24 | 8 |  |  | 32
3.2.2 |  |  |  |  | 24 | 8 |  |  | 32
3.2.3 |  |  |  |  | 24 | 120 |  |  | 144
2.2 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | [6 empty] | 24 | 56 | 80
2.2.2 | [6 empty] | 24 | 48 | 72
2.2.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 80 | 112 | 192
4.3.2 | [6 empty] | 0 | 0 | 0
Total | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
PHASE 7 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 0 | 0 | 0
4.3.2 | [6 empty] | 80 | 112 | 192
Total | 64 | 160 | 152 | 152 | 72 | 136 | 80 | 112 | 928
PHASE 8 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 24 | 8 |  |  | 32
8.2.2 |  |  |  |  | 24 | 8 |  |  | 32
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 10 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40
9.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 11 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8
11.2.1 |  | 32 |  | 8 |  |  |  |  | 40
11.2.2 |  | 8 |  | 104 |  |  |  |  | 112
11.2.3 |  | 16 |  | 16 |  |  |  |  | 32
11.2.4 |  | 24 |  | 24
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 896
PHASE 12 | 16 | [7 empty] | 16
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 13 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
Total (hours) | 688 | 1216 | 1648 | 456 | 576 | 1088 | 880 | 1744 | 8296
Total (days) | 86 | 152 | 206 | 57 | 72 | 136 | 110 | 218 | 1037

## Milestone 3 (hidden)
|  | DEV Team |  |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Effort
PHASE 1 | 16 | [7 empty] | 16
1.1 | 16 | [5 empty] | 0 | 0 | 176
1.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0
1.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0
Total | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 192
PHASE 2 | 16 | [7 empty] | 16
2.1 | 16 | [7 empty] | 16
2.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 16 | [7 empty] | 16
1.2.1 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 16 | [7 empty] | 16
3.1 | 16 | [7 empty] | 16
3.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 16 | [7 empty] | 16
1.3.1 |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 16 | [7 empty] | 16
4.1 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 |  | 32 | 8 | [5 empty] | 40
4.1.2 |  | 8 | 104 | [5 empty] | 112
4.1.3 |  | 16 | 16 | [5 empty] | 32
4.1.4 |  | 24 | 24 | [5 empty] | 48
4.2 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 |  |  |  |  | 24 | 8 |  |  | 32
3.2.2 |  |  |  |  | 24 | 8 |  |  | 32
3.2.3 |  |  |  |  | 24 | 120 |  |  | 144
2.2 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | [6 empty] | 24 | 56 | 80
2.2.2 | [6 empty] | 24 | 48 | 72
2.2.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 80 | 112 | 192
4.3.2 | [6 empty] | 0 | 0 | 0
Total | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
PHASE 7 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 0 | 0 | 0
4.3.2 | [6 empty] | 80 | 112 | 192
Total | 64 | 160 | 152 | 152 | 72 | 136 | 80 | 112 | 928
PHASE 8 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 48 | 8 |  |  | 56
8.2.2 |  |  |  |  | 48 | 8 |  |  | 56
8.2.3 |  |  |  |  | 48 | 120 |  |  | 168
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 144 | 136 | 72 | 152 | 824
PHASE 10 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40
8.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
8.2.1 |  |  |  |  | 0 | 8 |  |  | 8
8.2.2 |  |  |  |  | 0 | 8 |  |  | 8
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 24 | 136 | 72 | 152 | 704
PHASE 11 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8
11.2.1 |  | 32 |  | 8 |  |  |  |  | 40
11.2.2 |  | 8 |  | 104 |  |  |  |  | 112
11.2.3 |  | 16 |  | 16 |  |  |  |  | 32
11.2.4 |  | 24 |  | 24 |  |  |  |  | 48
9.2 | 16 |  |  | 0 |  |  | 0 |  | 16
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 944
PHASE 12 | 16 | [7 empty] | 16
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 13 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
Total (hours) | 688 | 1216 | 1648 | 456 | 600 | 1088 | 880 | 1744 | 8320
Total (days) | 86 | 152 | 206 | 57 | 75 | 136 | 110 | 218 | 1040