## Effort
|  | DEV Team |  |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Effort
PHASE 1 | 16 | [7 empty] | 16
1.1 | 16 | [5 empty] | 0 | 0 | 176
1.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0
1.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0
Total | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 192
PHASE 2 | 16 | [7 empty] | 16
2.1 | 16 | [7 empty] | 16
2.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 16 | [7 empty] | 16
1.2.1 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 16 | [7 empty] | 16
3.1 | 16 | [7 empty] | 16
3.1.1 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 16 | [7 empty] | 16
1.3.1 |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 16 | [7 empty] | 16
4.1 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 |  | 32 | 8 | [5 empty] | 40
4.1.2 |  | 8 | 104 | [5 empty] | 112
4.1.3 |  | 16 | 16 | [5 empty] | 32
4.1.4 |  | 24 | 24 | [5 empty] | 48
4.2 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 |  |  |  |  | 24 | 8 |  |  | 32
3.2.2 |  |  |  |  | 24 | 8 |  |  | 32
3.2.3 |  |  |  |  | 24 | 120 |  |  | 144
2.2 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | [6 empty] | 24 | 56 | 80
2.2.2 | [6 empty] | 24 | 48 | 72
2.2.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 80 | 112 | 192
4.3.2 | [6 empty] | 0 | 0 | 0
Total | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
PHASE 7 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 0 | 0 | 0
4.3.2 | [6 empty] | 80 | 112 | 192
Total | 64 | 160 | 152 | 152 | 72 | 136 | 80 | 112 | 928
PHASE 8 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 48 | 8 |  |  | 56
8.2.2 |  |  |  |  | 48 | 8 |  |  | 56
8.2.3 |  |  |  |  | 48 | 120 |  |  | 168
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72
Total | 64 | 104 | 152 | 0 | 144 | 136 | 72 | 152 | 824
PHASE 10 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40
8.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56
8.2.1 |  |  |  |  | 0 | 8 |  |  | 8
8.2.2 |  |  |  |  | 0 | 8 |  |  | 8
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 24 | 136 | 72 | 152 | 704
PHASE 11 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8
11.2.1 |  | 32 |  | 8 |  |  |  |  | 40
11.2.2 |  | 8 |  | 104 |  |  |  |  | 112
11.2.3 |  | 16 |  | 16 |  |  |  |  | 32
11.2.4 |  | 24 |  | 24 |  |  |  |  | 48
9.2 | 16 |  |  | 0 |  |  | 0 |  | 16
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 944
PHASE 12 | 16 | [7 empty] | 16
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 13 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72
Total | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
Total (hours) | 688 | 1216 | 1648 | 456 | 600 | 1088 | 880 | 1744 | 8320
Total (days) | 86 | 152 | 206 | 57 | 75 | 136 | 110 | 218 | 1040

## Cost
0 | Team Cost | [8 empty] | Travel costs | [5 empty] | Team Cost
|  | DEV Team |  |  | DATA team |  | IT team |  |  |  | DATA Team |  | IT Team |  |  |  | DEV Team |  |  | DATA team |  | IT team
Activity ID | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Total cost Team | Project Manager | Senior | Junior | Senior | Junior | Total Budget travel | Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Total cost Team
PHASE 1 | 400 | [7 empty] | 400 | [6 empty] | 16 | [7 empty] | 16
1.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 |  | 0 |  | 0 | 0 | 0 | 16 | [5 empty] | 0 | 0 | 176
1.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 104 | 0 | 0 | 0 | 0 | 0
1.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24 | 8 | 0 | 0 | 0 | 0 | 0
1.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 24 | 0 | 0 | 0 | 0 | 0
Total | 800 | 4320 | 8640 | 0 | 0 | 0 | 0 | 0 | 13760 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 72 | 144 | 0 | 0 | 0 | 0 | 0 | 192
PHASE 2 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
2.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
2.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 |  | 24 | 8 | 0 | 0 |  |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 |  | 8 | 104 | 0 | 0 |  |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
2.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 |  | 24 | 8 | 0 | 0 |  |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
2.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 |  | 16 | 24 | 0 | 0 |  |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
1.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 |  | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 |  | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 32
1.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 |  | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 24 | 120 | 0 | 0 | 144
Total | 1200 | 4320 | 8640 | 0 | 4140 | 5780 | 0 | 0 | 24080 | 48 | 72 | 144 | 0 | 72 | 48 | 48 | 72 | 144 | 0 | 72 | 136 | 0 | 0 | 472
PHASE 3 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
3.1 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
3.1.1 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 |  | 24 | 8 | 0 | 0 |  |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 |  | 8 | 104 | 0 | 0 |  |  | 8 | 104 | 0 | 0 | 0 | 0 | 0 | 112
3.1.3 | 0 | 1440 | 480 | 0 | 0 | 0 | 0 | 0 | 1920 |  | 24 | 8 | 0 | 0 |  |  | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 32
3.1.4 | 0 | 960 | 1440 | 0 | 0 | 0 | 0 | 0 | 2400 |  | 16 | 24 | 0 | 0 |  |  | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 40
1.3 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 80
1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 72
Total | 1200 | 4320 | 8640 | 0 | 0 | 0 | 4320 | 6840 | 25320 | 48 | 72 | 144 | 0 | 0 | 48 | 48 | 72 | 144 | 0 | 0 | 0 | 72 | 152 | 488
PHASE 4 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
4.1 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 8 |  |  |  | 0 | 8 | 8 |  |  |  | 0 |  | 0 |  | 8
4.1.1 | 0 | 1920 | 480 | 0 | 0 | 0 | 0 | 0 | 2400 |  | 32 | 8 |  |  |  |  | 32 | 8 | [5 empty] | 40
4.1.2 | 0 | 480 | 6240 | 0 | 0 | 0 | 0 | 0 | 6720 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
4.1.3 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 1920 |  | 16 | 16 |  |  |  |  | 16 | 16 | [5 empty] | 32
4.1.4 | 0 | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 2880 |  | 24 | 24 |  |  |  |  | 24 | 24 | [5 empty] | 48
4.2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 8 |  |  |  | 0 | 8 | 8 |  |  |  | 0 |  | 0 |  | 8
4.2.1 | 0 | 1920 | 0 | 200 | 0 | 0 | 0 | 0 | 2120 |  | 32 |  | 8 |  |  |  | 32 |  | 8 |  |  |  |  | 40
4.2.2 | 0 | 480 | 0 | 2600 | 0 | 0 | 0 | 0 | 3080 |  | 8 |  | 104 |  |  |  | 8 |  | 104 |  |  |  |  | 112
4.2.3 | 0 | 960 | 0 | 400 | 0 | 0 | 0 | 0 | 1360 |  | 16 |  | 16 |  |  |  | 16 |  | 16 |  |  |  |  | 32
4.2.4 | 0 | 1440 | 0 | 600 | 0 | 0 | 0 | 0 | 2040 |  | 24 |  | 24 |  |  |  | 24 |  | 24 |  |  |  |  | 48
3.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 16 | 0 |  |  |  | 16 | 16 | 0 |  |  |  |  | 0 |  | 16
3.2.1 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
3.2.2 | 0 | 0 | 0 | 0 | 1380 | 340 | 0 | 0 | 1720 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
3.2.3 | 0 | 0 | 0 | 0 | 1380 | 5100 | 0 | 0 | 6480 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
2.2 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2520 | 3960 | [12 empty] | 24 | 56 | 80
2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | [12 empty] | 24 | 48 | 72
2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 2160 | 3600 | [12 empty] | 24 | 48 | 72
Total | 1600 | 9600 | 9120 | 3800 | 4140 | 5780 | 4320 | 6840 | 45200 | 64 | 160 | 152 | 152 | 72 | 64 | 64 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 960
PHASE 5 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
5.1 | 16 |  |  |  | 0 |  | 0 |  | 16 | 16 |  |  |  | 0 | 16 | 16 |  |  |  | 0 |  | 0 |  | 16
5.1.1 |  | 56 | 8 | [5 empty] | 64 |  | 56 | 8 |  |  |  |  | 56 | 8 | [5 empty] | 64
5.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
5.1.3 |  | 24 | 16 | [5 empty] | 40 |  | 24 | 16 |  |  |  |  | 24 | 16 | [5 empty] | 40
5.1.4 |  | 16 | 24 | [5 empty] | 40 |  | 16 | 24 |  |  |  |  | 16 | 24 | [5 empty] | 40
3.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
3.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
3.3.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
3.3.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 432 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 912 | 48 | 104 | 152 | 0 | 0 | 48 | 48 | 104 | 152 | 0 | 0 | 0 | 72 | 152 | 528
PHASE 6 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
6.1 | 16 |  |  |  | 0 |  | 0 |  | 16 | 16 |  |  |  | 0 | 16 | 16 |  |  |  | 0 |  | 0 |  | 16
6.1.1 |  | 56 | 8 | [5 empty] | 64 |  | 56 | 8 |  |  |  |  | 56 | 8 | [5 empty] | 64
6.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
6.1.3 |  | 24 | 16 | [5 empty] | 40 |  | 24 | 16 |  |  |  |  | 24 | 16 | [5 empty] | 40
5.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56 | 16 | 16 | 24 |  |  | 16 | 16 | 16 | 24 |  |  |  | 0 |  | 56
5.2.1 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
5.2.2 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
5.2.3 |  |  |  |  | 24 | 120 |  |  | 144 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
4.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
4.3.1 | [6 empty] | 40 | 56 | 96 | [12 empty] | 40 | 56 | 96
4.3.2 | [6 empty] | 40 | 56 | 96 | [12 empty] | 40 | 56 | 96
Total | 448 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 1104 | 64 | 104 | 152 | 0 | 72 | 64 | 64 | 104 | 152 | 0 | 72 | 136 | 80 | 112 | 720
PHASE 7 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
7.1 | 8 |  |  |  | 0 |  | 0 |  | 8 | 8 |  |  |  | 0 | 8 | 8 |  |  |  | 0 |  | 0 |  | 8
7.1.1 |  | 32 | 8 | [5 empty] | 40 |  | 32 | 8 |  |  |  |  | 32 | 8 | [5 empty] | 40
7.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
7.1.3 |  | 16 | 16 | [5 empty] | 32 |  | 16 | 16 |  |  |  |  | 16 | 16 | [5 empty] | 32
7.1.4 |  | 24 | 24 | [5 empty] | 48 |  | 24 | 24 |  |  |  |  | 24 | 24 | [5 empty] | 48
7.2 | 8 |  |  |  | 0 |  | 0 |  | 8 | 8 |  |  |  | 0 | 8 | 8 |  |  |  | 0 |  | 0 |  | 8
7.2.1 |  | 32 |  | 8 |  |  |  |  | 40 |  | 32 |  | 8 |  |  |  | 32 |  | 8 |  |  |  |  | 40
7.2.2 |  | 8 |  | 104 |  |  |  |  | 112 |  | 8 |  | 104 |  |  |  | 8 |  | 104 |  |  |  |  | 112
7.2.3 |  | 16 |  | 16 |  |  |  |  | 32 |  | 16 |  | 16 |  |  |  | 16 |  | 16 |  |  |  |  | 32
7.2.4 |  | 24 |  | 24 |  |  |  |  | 48 |  | 24 |  | 24 |  |  |  | 24 |  | 24 |  |  |  |  | 48
5.3 | 16 | 0 |  |  |  |  | 0 |  | 16 | 16 | 0 |  |  |  | 16 | 16 | 0 |  |  |  |  | 0 |  | 16
5.3.1 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
5.3.2 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
5.3.3 |  |  |  |  | 24 | 120 |  |  | 144 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
Total | 432 | 160 | 152 | 152 | 72 | 136 | 0 | 0 | 1104 | 48 | 160 | 152 | 152 | 72 | 48 | 48 | 160 | 152 | 152 | 72 | 136 | 0 | 0 | 720
PHASE 8 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
8.1 | 16 |  |  |  | 0 |  | 0 |  | 16 | 16 |  |  |  | 0 | 16 | 16 |  |  |  | 0 |  | 0 |  | 16
8.1.1 |  | 56 | 8 | [5 empty] | 64 |  | 56 | 8 |  |  |  |  | 56 | 8 | [5 empty] | 64
8.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
8.1.3 |  | 24 | 16 | [5 empty] | 40 |  | 24 | 16 |  |  |  |  | 24 | 16 | [5 empty] | 40
8.1.4 |  | 16 | 24 | [5 empty] | 40 |  | 16 | 24 |  |  |  |  | 16 | 24 | [5 empty] | 40
6.2 | 16 | 0 |  |  |  |  | 0 |  | 16 | 16 | 0 |  |  |  | 16 | 16 | 0 |  |  |  |  | 0 |  | 16
6.2.1 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
6.2.2 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
6.2.3 |  |  |  |  | 24 | 120 |  |  | 144 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
5.4 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
5.4.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
5.4.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
5.4.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 448 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 1136 | 64 | 104 | 152 | 0 | 72 | 64 | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 9 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
9.1 | 16 |  |  |  | 0 |  | 0 |  | 16 | 16 |  |  |  | 0 | 16 | 16 |  |  |  | 0 |  | 0 |  | 16
9.1.1 |  | 56 | 8 | [5 empty] | 64 |  | 56 | 8 |  |  |  |  | 56 | 8 | [5 empty] | 64
9.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
9.1.3 |  | 24 | 16 | [5 empty] | 40 |  | 24 | 16 |  |  |  |  | 24 | 16 | [5 empty] | 40
9.1.4 |  | 16 | 24 | [5 empty] | 40 |  | 16 | 24 |  |  |  |  | 16 | 24 | [5 empty] | 40
8.2 | 16 | 0 |  |  |  |  | 0 |  | 16 | 16 | 0 |  |  |  | 16 | 16 | 0 |  |  |  |  | 0 |  | 16
8.2.1 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
8.2.2 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
8.2.3 |  |  |  |  | 24 | 120 |  |  | 144 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
6.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
6.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
6.3.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
6.3.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 448 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 1136 | 64 | 104 | 152 | 0 | 72 | 64 | 64 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 10 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
10.1 | 16 |  |  |  | 0 |  | 0 |  | 16 | 16 |  |  |  | 0 | 16 | 16 |  |  |  | 0 |  | 0 |  | 16
10.1.1 |  | 56 | 8 | [5 empty] | 64 |  | 56 | 8 |  |  |  |  | 56 | 8 | [5 empty] | 64
10.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
10.1.3 |  | 24 | 16 | [5 empty] | 40 |  | 24 | 16 |  |  |  |  | 24 | 16 | [5 empty] | 40
9.2 | 16 | 16 | 24 |  |  |  | 0 |  | 56 | 16 | 16 | 24 |  |  | 16 | 16 | 16 | 24 |  |  |  | 0 |  | 56
9.2.1 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
9.2.2 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
9.2.3 |  |  |  |  | 24 | 120 |  |  | 144 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
7.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
7.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
7.3.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
7.3.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 48 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 1136 | 48 | 104 | 152 | 0 | 72 | 48 | 48 | 104 | 152 | 0 | 72 | 136 | 72 | 152 | 752
PHASE 11 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
11.1 | 8 |  |  |  | 0 |  | 0 |  | 8 | 8 |  |  |  | 0 | 8 | 8 |  |  |  | 0 |  | 0 |  | 8
11.1.1 |  | 32 | 8 | [5 empty] | 40 |  | 32 | 8 |  |  |  |  | 32 | 8 | [5 empty] | 40
11.1.2 |  | 8 | 104 | [5 empty] | 112 |  | 8 | 104 |  |  |  |  | 8 | 104 | [5 empty] | 112
11.1.3 |  | 16 | 16 | [5 empty] | 32 |  | 16 | 16 |  |  |  |  | 16 | 16 | [5 empty] | 32
11.1.4 |  | 24 | 24 | [5 empty] | 48 |  | 24 | 24 |  |  |  |  | 24 | 24 | [5 empty] | 48
11.2 | 8 |  |  |  | 0 |  | 0 |  | 8 | 8 |  |  |  | 0 | 8 | 8 |  |  |  | 0 |  | 0 |  | 8
11.2.1 |  | 32 |  | 8 |  |  |  |  | 40 |  | 32 |  | 8 |  |  |  | 32 |  | 8 |  |  |  |  | 40
11.2.2 |  | 8 |  | 104 |  |  |  |  | 112 |  | 8 |  | 104 |  |  |  | 8 |  | 104 |  |  |  |  | 112
11.2.3 |  | 16 |  | 16 |  |  |  |  | 32 |  | 16 |  | 16 |  |  |  | 16 |  | 16 |  |  |  |  | 32
11.2.4 |  | 24 |  | 24 | [6 empty] | 24 |  | 24 |  |  |  | 24 |  | 24
10.2 | 16 |  |  | 0 |  |  | 0 |  | 16 | 16 |  |  | 0 |  | 16 | 16 |  |  | 0 |  |  | 0 |  | 16
10.2.1 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
10.2.2 |  |  |  |  | 24 | 8 |  |  | 32 |  |  |  |  | 24 | [5 empty] | 24 | 8 |  |  | 32
10.2.3 |  |  |  |  | 24 | 120 |  |  | 144 |  |  |  |  | 24 | [5 empty] | 24 | 120 |  |  | 144
8.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
8.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
8.3.1 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
8.3.1 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 896 | 48 | 160 | 152 | 152 | 72 | 48 | 48 | 160 | 152 | 152 | 72 | 136 | 72 | 152 | 896
PHASE 12 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
9.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
9.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
9.3.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
9.3.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 416 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 640 | 32 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 13 | 400 | [7 empty] | 400 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
10.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
10.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
10.3.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
10.3.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 416 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 640 | 32 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256
PHASE 14 | 400 | [7 empty] | 16 | 16 |  |  |  |  | 16 | 16 | [7 empty] | 16
11.3 | 16 | 0 |  |  | 0 |  |  |  | 16 | 16 | 0 |  |  | 0 | 16 | 16 | 0 |  |  | 0 |  |  |  | 16
11.3.1 | [6 empty] | 24 | 56 | 80 | [12 empty] | 24 | 56 | 80
11.3.2 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
11.3.3 | [6 empty] | 24 | 48 | 72 | [12 empty] | 24 | 48 | 72
Total | 416 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256 | 32 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 72 | 152 | 256

## RiferimentiCosti
Team Cost | [8 empty] | Travel costs
| DEV Team |  |  | DATA team |  | IT team |  |  |  | DATA Team |  | IT Team |  |  | DEV Team |  | DATA team |  | IT team
Project Manager | Senior | Backend | Frontend | Senior | Junior | Senior | Junior | Total cost Team | Project Manager | Senior | Junior | Senior | Junior | Total Budget travel | Development Software | Cloud Services | Software Data | Cloud Servicies | Cloud Servicies | Total cost Team
25 | 60 | 60 | 25 | 57.5 | 42.5 | 60 | 45 |  | 120 | 150 | 140 | 150 | 140 |  | 50 | 300 | 30 | 250 | 300
per ora | per ora | per ora | per ora | per ora | per ora | per ora | per ora |  | per gg (/8 h) | per gg (/8h) | per gg (/8h) | per gg (/8h) | per gg (/8h) |  | per gg (/8h) | per gg (/8h) | per gg (/8h) | per gg (/8h) | per gg (/8h)
[9 empty] | 200 | 150 | 150 | 200 | 200
[9 empty] | per sprint | per week | per week | per week | per week